Table 1 - Phase Distribution of Effort: Organic Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 6% | 6% | 6% | 6% |
| Product Design | 16 | 16 | 16 | 16 |
| Detailed Design | 26 | 25 | 24 | 23 |
| Code & Unit Test | 42 | 40 | 38 | 36 |
| Integration & Test | 16 | 19 | 22 | 25 |
| Total: | 100 | 100 | 100 | 100 |

Table 2 - Phase Distribution of Schedule: Oraganic Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 10% | 11% | 12% | 13% |
| Product Design | 19 | 19 | 19 | 19 |
| Detailed Design & Code & Unit Test | 63 | 59 | 55 | 51 |
| Integration & Test | 18 | 22 | 26 | 30 |
| Total: | 100 | 100 | 100 | 100 |

Table 3 - Phase Distribution of Effort: Semidetached Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 7% | 7% | 7% | 7% |
| Product Design | 17 | 17 | 17 | 17 |
| Detailed Design | 27 | 26 | 25 | 24 |
| Code & Unit Test | 37 | 35 | 33 | 31 |
| Integration & Test | 19 | 22 | 25 | 28 |
| Total: | 100 | 100 | 100 | 100 |

Table 4 - Phase Distribution of Schedule: Semidetached Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 16% | 18% | 20% | 22% |
| Product Design | 24 | 25 | 26 | 27 |
| Detailed Design & Code & Unit Test | 56 | 52 | 48 | 44 |
| Integration & Test | 20 | 23 | 26 | 29 |
| Total: | 100 | 100 | 100 | 100 |

Table 5 - Phase Distribution of Effort: Embedded Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 8% | 8% | 8% | 8% |
| Product Design | 18 | 18 | 18 | 18 |
| Detailed Design | 28 | 27 | 26 | 25 |
| Code & Unit Test | 32 | 30 | 28 | 26 |
| Integration & Test | 22 | 25 | 28 | 31 |
| Total: | 100 | 100 | 100 | 100 |

Table 6 - Phase Distribution of Schedule: Embedded Mode

| Phase | Small ( 2 KDSI) | Intermediate(8 KDSI) | Medium( 32 KDSI ) | Large( 128 KDSI ) |
| --- | --- | --- | --- | --- |
| Plans & Requirements | 24% | 28% | 32% | 36% |
| Product Design | 30 | 32 | 34 | 36 |
| Detailed Design & Code & Unit Test | 48 | 44 | 40 | 36 |
| Integration & Test | 22 | 24 | 26 | 28 |
| Total: | 100 | 100 | 100 | 100 |